## Sheet1
Suggested Structure for Excel Document:
Tab 1: Master Tracker
Task Name | Description/Details | Responsible Team/Person | Status | Start Date | Due Date | Notes/Next Steps
Workflow 1: SFTP | Transfer data to SFTP | Qualtrics Support Team | In Progress | 2024-09-18 | 2024-09-20 | Follow up with file integration
Workflow 2: Merge Data | Combine SFTP data with Directory fields | Internal Data Team | Pending |  |  | Awaiting data structure
Workflow 3: Sampling | Create sample from merged data | Product Team | Completed | 2024-09-15 | 2024-09-17 | Final testing done
Survey Programming | Build survey, define flow, and raise concerns | Product/Survey Team | In Progress | 2024-09-18 | 2024-09-22 | Initial draft done
Email Invite | Send invite for the survey | Qualtrics Support Team | Pending |  |  | Prepare email content
Dashboard | Design dashboard for survey results | Product Team | Pending
TextiQ (optional) | Implement TextiQ for feedback analysis | Internal/Qualtrics Team | Pending |  |  | Evaluate feasibility
Tab 2: Team Assignments
Team Name | Key Responsibilities | Contact Person | Notes
Qualtrics Support Team | File transfer, email invites, TextiQ setup | John Doe | Follow-up on Workflow 1
Internal Data Team | Merging data, verifying fields | Jane Smith | Identify necessary fields for merge
Product Team | Sampling, survey build, dashboard setup | Mike Brown | Survey flow completion required